## Sheet1
Week | <component>
| BE | FE
2023-01-08 | Collect requirement about system to build system (respond time, load balance...) | Collect/tranfer requirement from customer to build system
2023-01-15 |  |  |  |  | Difficulty | Hard
2023-01-22 | Collect data for traning model | Collect data from end user to build a criteria form |  |  |  | Medium
2023-01-29 | [5 empty] | Easy
2023-02-05 | Implement CI | Implement CI
2023-02-12
2023-02-19 | Training model (1st) | Build common UI component
2023-02-26
2023-03-05 | Training model (2nd) | Build form of select and combine house criteria
2023-03-12
2023-03-19 | Training model (3rd) | Combine all UI to make a complete system
2023-03-26
2023-04-02 | Build API | Testing UI, UX
2023-04-09
2023-04-16 | Demo API | Demo UI, UX | Quarterly plan
2023-04-23 | Implement CD | Implement CD
2023-04-30
2023-05-07 | Handle throw error/exception in BE system | Integration with API
2023-05-14
2023-05-21 | Integration with FE
2023-05-28 |  | Handle error/exception in FE system
2023-06-04
2023-06-11 | Integration test
2023-06-18
2023-06-25 | Release | Release | Quarterly plan | Yearly plan
| Goals | Goals
| A system power by ML provide ability for predict house price in Boston through API base on some input of user | An user interface with friendly user experience provide to end-user abitility of select and combine some condition about house-feature/house amenities and provide to end-user prediction price of house base on selected criteria through Bakhend API